## Read me
SEO roadmap template
From passieon.com. Free to use and change. Nothing in it is gated.
The rule the whole template is built on
The roadmap runs backwards from the enquiries the business needs by month six. Set the goal in enquiries, calls, bookings or sales first (the Goals tab), then plan the months that get there. A roadmap with no enquiry line is a list of tasks, and a client cannot hold anyone to a list of tasks.
How to use it
1. Goals: the five numbers at month zero, from the accounts the client owns, and the target for month six.
2. Roadmap: the six months, each with its stage, its work, the page each item touches and what it needs from the client. The suggested rows are a starting shape; replace them with the client's own pages.
3. Backlog: every candidate piece of work, scored by what it does for enquiries and what it costs in hours, then given a month or dropped.
4. From the client: everything only the client can supply, with the date asked and the date received, because the roadmap slips exactly as long as these do.
5. Quarterly review: what moved, what was done, what comes next, and the decision. The monthly report (passieon.com/blog/seo-report-template/) checks the roadmap every month.
What never goes in
A ranking as a goal. A month with no named page. A task nobody owns. A promise about when Google will do anything. A fee.

## Goals
Goals, in the order they matter
Client
Roadmap starts
Prepared by
The five numbers | Month 0 | Month 3 target | Month 6 target | Month 6 actual | Where it is measured
Enquiries traced to search, per month |  |  |  |  | The enquiry log: calls, forms and bookings that came from a search
Calls from the Business Profile, per month |  |  |  |  | Business Profile, Insights, Calls
Clicks from Google, per month |  |  |  |  | Search Console, Performance, total clicks
Impressions, per month |  |  |  |  | Search Console, Performance, total impressions
Pages indexed |  |  |  |  | Search Console, Pages, Indexed
Enquiries come first because they are the only line the client will act on. Rankings are not a goal: a ranking report is the easiest thing in the industry to make look good, and an enquiry cannot be faked that way.

## Roadmap
Month | Stage | Kind | The work | The page it touches | What it needs from the client | Status | Done (date) | What changed in enquiries
1 | Foundations | profile | Claim or verify the Business Profile; primary category set to the main service; hours, address, phone and the website link checked | the Business Profile | access to the profile | planned
1 | Foundations | technical | One host answering (https, one hostname, three redirects); sitemap submitted; robots and canonicals checked; every money page indexed or the reason found | the whole site | Search Console access | planned
1 | Foundations | tracking | Enquiries logged by source: form, call, profile, chat; the test submission from a phone | the contact page and every form | the inbox the form sends to | planned
1 | Foundations | page | The money pages audited: one search each, title, description, one H1, a call to action near the top | the home page and every service page | an hour to approve changes | planned
1 | Foundations
1 | Foundations
2 | The pages that earn | page | One page per service the business sells and does not yet have a page for | new service pages | confirmation of which services are offered | planned
2 | The pages that earn | page | Area pages only where the business genuinely serves the place, each with something true about that place | area pages | the towns actually served | planned
2 | The pages that earn | citations | Name, address and phone identical on the profile, the site and the main directories | the footer, the profile, the directories | nothing | planned
2 | The pages that earn | reviews | A review request sent after every job, by text, with the link; every review answered within the week | the profile | who sends the request, and to whom | planned
2 | The pages that earn
2 | The pages that earn
3 | Proof and conversion | content | Photographs of the real work and the real team on the service pages | service pages | twenty phone photographs from real jobs | planned
3 | Proof and conversion | page | The enquiry path tested again on a phone: the number in the header, the form sending, the confirmation telling the truth | every page | nothing | planned
3 | Proof and conversion | content | The first two guides answering the questions customers ask before they call, each linking to the service it feeds | guides | the questions customers actually ask | planned
3 | Proof and conversion | tracking | The first monthly report: enquiries traced to search, calls from the profile, clicks, impressions, pages indexed | the report | the month of calls that came from a search | planned
3 | Proof and conversion
3 | Proof and conversion
4 | The competitive searches | page | The two or three searches that would change the business, each given the best page in its market | the pages for those searches | agreement on which searches matter | planned
4 | The competitive searches | links | One page worth linking to: a tool, a dataset or a guide with sourced figures, measured against what the linkers in the niche already cite | a new page | nothing | planned
4 | The competitive searches | reviews | Review count and reply rate checked against the nearest competitors | the profile | nothing | planned
4 | The competitive searches
4 | The competitive searches
5 | Supporting content | content | Guides that support the competitive pages, each linking to the page it supports from its body | guides | an hour to approve | planned
5 | Supporting content | technical | Speed measured on field data on the home page and a service page; the largest image fixed first | the slowest pages | nothing | planned
5 | Supporting content | citations | Links lost since month one asked for back; dead linked pages redirected | old addresses | nothing | planned
5 | Supporting content
5 | Supporting content
6 | Review and the next six | tracking | Six months of enquiries against the month-zero baseline, page by page | the report | the enquiry records | planned
6 | Review and the next six | page | Pages with no impressions in six months merged or removed with a redirect | thin pages | nothing | planned
6 | Review and the next six | other | The next six months planned from what earned and what did not | the roadmap | a call | planned
6 | Review and the next six
6 | Review and the next six
The suggested rows are a starting shape, written for a local service business; replace them with the client's own pages and delete what does not apply. A month with no named page is a month nobody can hold you to.

## Backlog
Item | Kind | The search it serves, if a page | Enquiry impact (1 now, 2 clicks, 3 later) | Effort (hours) | Month | Status | Notes
Everything that could be done goes here first; the Roadmap takes what the enquiry impact and the hours justify. Impact 1 costs enquiries now (a form that does not send, a service with no page), 2 costs clicks, 3 can wait.

## From the client
What is needed | For which month | Asked on | Received on | Notes
Access to Search Console
Access to the Business Profile
Access to the website (or the developer who has it)
The inbox the enquiry form sends to, and who reads it
Which services are offered, by name
The towns actually served
Twenty phone photographs of real jobs and the real team
Who sends review requests, and to whom
An hour a month to approve pages
The questions customers ask before they call
The roadmap slips exactly as long as these do, so they are asked for in the first week and dated.

## Quarterly review
Quarter | What moved (enquiries, calls, clicks, against month 0) | What was done | What comes next, and why | Decision
Q1
Q2
Q3
Q4
Written with the Goals tab open. If enquiries did not move, the next quarter changes; if they did, it says which pages moved them.